## Sheet1
Photo Synthesis Project Plan - CS231n | 2017-04-24 | 2017-05-01 | 2017-05-08 | 2017-05-15 | 2017-05-22 | 2017-05-29 | 2017-06-05
| Updated: | 2017-04-26 |  |  | Design | Build | Complete
PLAN / PROPOSAL
Submit proposal | bar: 2017-04-24
Get input via private Piazza post | bar: 2017-04-24 to 2017-05-01
DATA
Confirm same data sets as paper | bar: 2017-04-24 to 2017-05-01
Create own small subset for system test | bar: 2017-04-24 to 2017-05-01
COMPUTE ENVIRONMENT
Initial cloud compute setup (installs, GPU, github, data) | bar: 2017-04-24 to 2017-05-01
Data transfer to cloud and batch run process (tmux, etc.) | bar: 2017-04-24 to 2017-05-01
Local environments setup (our macs) | bar: 2017-04-24 to 2017-05-01
DATA PRE-PROCESSING
Confirm same pre-processed data as paper | bar: 2017-04-24 to 2017-05-01
Additional pre-processing | bar: 2017-05-01 to 2017-05-08
RESULTS - MATCH PAPER (Target 1)
Stacked GAN | bar: 2017-04-24 to 2017-05-22
RESULTS - EXTEND PAPER (Target 2)
WGAN | bar: 2017-05-15 to 2017-05-29
PAPER (June 12)
1st draft | bar: 2017-05-15 to 2017-05-29
Results/plots | bar: 2017-05-22 to 2017-06-05
Final draft | [7 empty] | DUE 6/12 !!! | bar: 2017-05-29 to 2017-06-05
PRESENTATION (Week of June 5)
PPT / Keynote | bar: 2017-05-22 to 2017-06-05
Paper print (FedEx Office) | bar: 2017-06-05